## Dashboard
Academic Block (G+4 RCC) - Institutional Campus
CE725-CASE-01 ¦ data date: end of Period 6 (Sep-2026)
POSITION
Budget at completion (BAC)
Planned value (PV)
Earned value (EV)
Actual cost (AC)
Percent complete
Percent spent
VARIANCE
Cost variance (CV)
Schedule variance (SV)
| Cost performance index (CPI) | Rupees of budgeted work per rupee spent. Below 1.00 is overspending.
| Schedule performance index (SPI) | Work done per unit of work scheduled. Below 1.00 is behind.
FORECAST
| EAC — performance continues | BAC / CPI. The default forecast.
| EAC — variance was a one-off | AC + (BAC - EV). The most optimistic assumption available.
| EAC — cost and schedule pressure | AC + (BAC - EV) / (CPI x SPI). Recovering schedule normally costs money.
ETC (on EAC, performance continues)
VAC (on EAC, performance continues)
| TCPI to finish on budget | Efficiency the REMAINING work must achieve. Compare it with CPI.
| VERDICT | Thresholds: an index within 5% of plan is treated as noise.

## Inputs
Academic Block (G+4 RCC) - Institutional Campus — EVM Inputs
Yellow cells are editable. Change any of them and every index, forecast and chart in this workbook recalculates.
WBS ID | Work Package | Budget (Rs) | AC P1 | AC P2 | AC P3 | AC P4 | AC P5 | AC P6 | %C P1 | %C P2 | %C P3 | %C P4 | %C P5 | %C P6
1.1 | Site mobilisation and enabling works | 2500000 | 1500000 | 1200000 | 0 | 0 | 0 | 0 | 55% | 100% | 100% | 100% | 100% | 100%
1.2 | Site office, stores and labour accommodation | 1800000 | 950000 | 900000 | 0 | 0 | 0 | 0 | 50% | 100% | 100% | 100% | 100% | 100%
2.1 | Excavation and earthwork | 4200000 | 1100000 | 1500000 | 1650000 | 1100000 | 750000 | 0 | 20% | 45% | 72% | 90% | 100% | 100%
2.2 | PCC and footings | 6800000 | 0 | 1100000 | 1950000 | 2500000 | 1850000 | 0 | 0% | 15% | 42% | 78% | 100% | 100%
2.3 | Foundation RCC up to plinth | 9500000 | 0 | 0 | 1900000 | 3000000 | 3400000 | 2500000 | 0% | 0% | 18% | 46% | 80% | 100%
2.4 | Plinth beams and backfilling | 3800000 | 0 | 0 | 0 | 850000 | 1600000 | 1650000 | 0% | 0% | 0% | 20% | 62% | 100%
3.1 | RCC columns, ground to fourth floor | 14500000 | 0 | 0 | 0 | 0 | 1300000 | 2300000 | 0% | 0% | 0% | 0% | 8% | 22%
3.2 | RCC beams and slabs, ground to fourth floor | 21000000 | 0 | 0 | 0 | 0 | 1200000 | 2100000 | 0% | 0% | 0% | 0% | 5% | 14%
3.3 | Staircase and lift core RCC | 5500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
4.1 | Block masonry | 8800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
4.2 | Internal plaster | 5200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
4.3 | External plaster and texture finish | 4600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
4.4 | Flooring, vitrified tile and kota stone | 9500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
4.5 | Painting, internal and external | 6200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
5.1 | Internal electrification | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
5.2 | Plumbing and sanitary installation | 7200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
5.3 | HVAC and fire fighting | 9800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
6.1 | External development and landscaping | 5800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
6.2 | Testing, commissioning and handover | 2800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
TOTAL | bar: AC P1 to AC P6

## Baseline
Time-Phased Budget (Planned Value)
WBS ID | Work Package | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
1.1 | Site mobilisation and enabling works | 1250000 | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | Site office, stores and labour accommodation | 900000 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | Excavation and earthwork | 1400000 | 1400000 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2 | PCC and footings | 0 | 1762962.96 | 3274074.07 | 1762962.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3 | Foundation RCC up to plinth | 0 | 0 | 2462962.96 | 4574074.07 | 2462962.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.4 | Plinth beams and backfilling | 0 | 0 | 0 | 1900000 | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1 | RCC columns, ground to fourth floor | 0 | 0 | 0 | 0 | 1508000 | 3596000 | 4292000 | 3596000 | 1508000 | 0 | 0 | 0
3.2 | RCC beams and slabs, ground to fourth floor | 0 | 0 | 0 | 0 | 1555555.56 | 3888888.89 | 5055555.56 | 5055555.56 | 3888888.89 | 1555555.56 | 0 | 0
3.3 | Staircase and lift core RCC | 0 | 0 | 0 | 0 | 0 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 0 | 0
4.1 | Block masonry | 0 | 0 | 0 | 0 | 0 | 0 | 915200 | 2182400 | 2604800 | 2182400 | 915200 | 0
4.2 | Internal plaster | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 812500 | 1787500 | 1787500 | 812500
4.3 | External plaster and texture finish | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150000 | 1150000 | 1150000 | 1150000
4.4 | Flooring, vitrified tile and kota stone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2462962.96 | 4574074.07 | 2462962.96
4.5 | Painting, internal and external | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3100000 | 3100000
5.1 | Internal electrification | 0 | 0 | 0 | 0 | 0 | 0 | 777777.78 | 1944444.44 | 2527777.78 | 2527777.78 | 1944444.44 | 777777.78
5.2 | Plumbing and sanitary installation | 0 | 0 | 0 | 0 | 0 | 0 | 533333.33 | 1333333.33 | 1733333.33 | 1733333.33 | 1333333.33 | 533333.33
5.3 | HVAC and fire fighting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1531250 | 3368750 | 3368750 | 1531250
6.1 | External development and landscaping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1933333.33 | 1933333.33 | 1933333.33
6.2 | Testing, commissioning and handover | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800000
TOTAL

## EVM
Earned Value by Reporting Period
Data date: end of Period 6. EV and AC stop there; beyond it they return NA() so the charts break the line rather than plotting zero.
Period | Label | PV cum | EV cum | AC cum | CV | SV | CPI | SPI | % complete | % spent
1 | Apr-2026
2 | May-2026
3 | Jun-2026
4 | Jul-2026
5 | Aug-2026
6 | Sep-2026
7 | Oct-2026
8 | Nov-2026
9 | Dec-2026
10 | Jan-2027
11 | Feb-2027
12 | Mar-2027

## Variance
Cost and Schedule Variance by Work Package — Period 6
Where the project variance actually is. Only packages that have started.
WBS ID | Work Package | Budget | EV | AC | CV | CPI | % complete
2.1 | Excavation and earthwork | 4200000 | 4200000 | 6100000 | -1900000 | 0.68852 | 100%
2.3 | Foundation RCC up to plinth | 9500000 | 9500000 | 10800000 | -1300000 | 0.87963 | 100%
2.2 | PCC and footings | 6800000 | 6800000 | 7400000 | -600000 | 0.91892 | 100%
3.1 | RCC columns, ground to fourth floor | 14500000 | 3190000 | 3600000 | -410000 | 0.88611 | 22%
3.2 | RCC beams and slabs, ground to fourth floor | 21000000 | 2940000 | 3300000 | -360000 | 0.89091 | 14%
2.4 | Plinth beams and backfilling | 3800000 | 3800000 | 4100000 | -300000 | 0.92683 | 100%
1.1 | Site mobilisation and enabling works | 2500000 | 2500000 | 2700000 | -200000 | 0.92593 | 100%
1.2 | Site office, stores and labour accommodation | 1800000 | 1800000 | 1850000 | -50000 | 0.97297 | 100%

## Read Me
About this workbook
Exported from the CE725 EVM Dashboard for Academic Block (G+4 RCC) - Institutional Campus.
Data date: end of Period 6 (Sep-2026).
LIVE, NOT A SNAPSHOT
Every figure on the Dashboard and EVM sheets is an Excel formula. Edit any
yellow cell on Inputs or Baseline and the whole workbook recalculates. That
is the point: the numbers can be interrogated and re-run without the tool.
WHAT TO EDIT
Inputs budgets, actual cost per period, percent complete per period
Baseline the time-phased budget
Nothing else is meant to be typed into.
LIMITATIONS
1. Earned value is only as good as the percent-complete figures on the
Inputs sheet. Those are a judgement made at site. Neither this workbook
nor the tool can detect an optimistic one, and an optimistic percent
complete produces a confident, wrong EV.
2. There is one baseline. Re-baselining is not modelled.
3. Earned Schedule is computed in the dashboard application, not here.
4. The forecast assumes work continues. A suspended project needs a
re-baseline, not an extrapolation.
POSITION AT EXPORT
CPI 0.872 SPI 0.863 complete 24.8% spent 28.5%
These figures are stated here for reference only. The Dashboard sheet
recomputes them from the inputs and is what should be read.