## Read Me
Manual Benchmark Workbook — Earned Value Management
Project Academic Block (G+4 RCC) - Institutional Campus
Code CE725-CASE-01
BAC Rs 140,000,000.00
Baseline 12 monthly periods
Data date end of Period 6 (Sep-2026)
Benchmark reporting periods 5 and 6
PURPOSE
This workbook is the independent manual benchmark for the EVM dashboard.
Every earned value figure in it is produced by a typed Excel formula acting
on the raw inputs on the 'Inputs' and 'Baseline' sheets. Click any green cell
to see the arithmetic. No value here is copied from the Python tool.
WHAT IT PROVES
That two separately written implementations of the EVM definitions agree:
one in Python (the evm package), one in Excel formulas (this workbook).
An arithmetic or logic error in one will not be reproduced by the other.
WHAT IT DOES NOT PROVE
That the inputs are right. Both implementations read the same budgets,
percent-complete figures and costs. If a work package is reported at 60%
complete when it is actually 40% complete, both will agree on an earned
value that is wrong by Rs lakhs. No spreadsheet can detect that; only a
measurement at site can. This is the single most important limitation of
the whole tool and it is stated again in the user manual.
COLOUR KEY
Yellow typed raw input, the only hand-entered numbers in the workbook
Green computed by an Excel formula
Grey totals
SHEETS
Inputs budgets, actual cost per period, percent complete per period
Baseline the time-phased budget and the cumulative planned value curve
Calc P5 per-package earned value calculation at end of Period 5
Calc P6 per-package earned value calculation at end of Period 6
Indices all EVM indices and forecasts for both periods, side by side
Generated by benchmark/build_benchmark.py. The script places formulas;
Excel evaluates them.

## Inputs
Raw Inputs
Hand-entered data. Every other number in this workbook is derived from these cells.
WBS ID | Work Package | Budget (Rs) | AC P1 | AC P2 | AC P3 | AC P4 | AC P5 | AC P6 | %C P1 | %C P2 | %C P3 | %C P4 | %C P5 | %C P6
1.1 | Site mobilisation and enabling works | 2500000 | 1500000 | 1200000 | 0 | 0 | 0 | 0 | 55% | 100% | 100% | 100% | 100% | 100%
1.2 | Site office, stores and labour accommodation | 1800000 | 950000 | 900000 | 0 | 0 | 0 | 0 | 50% | 100% | 100% | 100% | 100% | 100%
2.1 | Excavation and earthwork | 4200000 | 1100000 | 1500000 | 1650000 | 1100000 | 750000 | 0 | 20% | 45% | 72% | 90% | 100% | 100%
2.2 | PCC and footings | 6800000 | 0 | 1100000 | 1950000 | 2500000 | 1850000 | 0 | 0% | 15% | 42% | 78% | 100% | 100%
2.3 | Foundation RCC up to plinth | 9500000 | 0 | 0 | 1900000 | 3000000 | 3400000 | 2500000 | 0% | 0% | 18% | 46% | 80% | 100%
2.4 | Plinth beams and backfilling | 3800000 | 0 | 0 | 0 | 850000 | 1600000 | 1650000 | 0% | 0% | 0% | 20% | 62% | 100%
3.1 | RCC columns, ground to fourth floor | 14500000 | 0 | 0 | 0 | 0 | 1300000 | 2300000 | 0% | 0% | 0% | 0% | 8% | 22%
3.2 | RCC beams and slabs, ground to fourth floor | 21000000 | 0 | 0 | 0 | 0 | 1200000 | 2100000 | 0% | 0% | 0% | 0% | 5% | 14%
3.3 | Staircase and lift core RCC | 5500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
4.1 | Block masonry | 8800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
4.2 | Internal plaster | 5200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
4.3 | External plaster and texture finish | 4600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
4.4 | Flooring, vitrified tile and kota stone | 9500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
4.5 | Painting, internal and external | 6200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
5.1 | Internal electrification | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
5.2 | Plumbing and sanitary installation | 7200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
5.3 | HVAC and fire fighting | 9800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
6.1 | External development and landscaping | 5800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
6.2 | Testing, commissioning and handover | 2800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
TOTAL | bar: AC P1 to AC P6
BAC (sum of work package budgets)

## Baseline
Time-Phased Budget (Planned Value)
Planned value per work package per baseline period. Row 'Cumulative PV' is the S-curve.
WBS ID | Work Package | PV P1 | PV P2 | PV P3 | PV P4 | PV P5 | PV P6 | PV P7 | PV P8 | PV P9 | PV P10 | PV P11 | PV P12 | Row total | Budget check
1.1 | Site mobilisation and enabling works | 1250000 | 1250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | Site office, stores and labour accommodation | 900000 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | Excavation and earthwork | 1400000 | 1400000 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2 | PCC and footings | 0 | 1762962.96 | 3274074.07 | 1762962.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3 | Foundation RCC up to plinth | 0 | 0 | 2462962.96 | 4574074.07 | 2462962.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.4 | Plinth beams and backfilling | 0 | 0 | 0 | 1900000 | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1 | RCC columns, ground to fourth floor | 0 | 0 | 0 | 0 | 1508000 | 3596000 | 4292000 | 3596000 | 1508000 | 0 | 0 | 0
3.2 | RCC beams and slabs, ground to fourth floor | 0 | 0 | 0 | 0 | 1555555.56 | 3888888.89 | 5055555.56 | 5055555.56 | 3888888.89 | 1555555.56 | 0 | 0
3.3 | Staircase and lift core RCC | 0 | 0 | 0 | 0 | 0 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 0 | 0
4.1 | Block masonry | 0 | 0 | 0 | 0 | 0 | 0 | 915200 | 2182400 | 2604800 | 2182400 | 915200 | 0
4.2 | Internal plaster | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 812500 | 1787500 | 1787500 | 812500
4.3 | External plaster and texture finish | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150000 | 1150000 | 1150000 | 1150000
4.4 | Flooring, vitrified tile and kota stone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2462962.96 | 4574074.07 | 2462962.96
4.5 | Painting, internal and external | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3100000 | 3100000
5.1 | Internal electrification | 0 | 0 | 0 | 0 | 0 | 0 | 777777.78 | 1944444.44 | 2527777.78 | 2527777.78 | 1944444.44 | 777777.78
5.2 | Plumbing and sanitary installation | 0 | 0 | 0 | 0 | 0 | 0 | 533333.33 | 1333333.33 | 1733333.33 | 1733333.33 | 1333333.33 | 533333.33
5.3 | HVAC and fire fighting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1531250 | 3368750 | 3368750 | 1531250
6.1 | External development and landscaping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1933333.33 | 1933333.33 | 1933333.33
6.2 | Testing, commissioning and handover | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800000
TOTAL
Cumulative PV (S-curve)
The final cumulative value must equal BAC exactly.

## Calc P5
Earned Value by Work Package — end of Period 5 (Aug-2026)
EV = cumulative percent complete x budget. PV and AC are cumulative to this period.
WBS ID | Work Package | Budget (Rs) | % Complete | EV (Rs) | PV cum (Rs) | AC cum (Rs) | CV (Rs) | SV (Rs) | CPI | SPI
1.1 | Site mobilisation and enabling works
1.2 | Site office, stores and labour accommodation
2.1 | Excavation and earthwork
2.2 | PCC and footings
2.3 | Foundation RCC up to plinth
2.4 | Plinth beams and backfilling
3.1 | RCC columns, ground to fourth floor
3.2 | RCC beams and slabs, ground to fourth floor
3.3 | Staircase and lift core RCC
4.1 | Block masonry
4.2 | Internal plaster
4.3 | External plaster and texture finish
4.4 | Flooring, vitrified tile and kota stone
4.5 | Painting, internal and external
5.1 | Internal electrification
5.2 | Plumbing and sanitary installation
5.3 | HVAC and fire fighting
6.1 | External development and landscaping
6.2 | Testing, commissioning and handover
PROJECT TOTAL

## Calc P6
Earned Value by Work Package — end of Period 6 (Sep-2026)
EV = cumulative percent complete x budget. PV and AC are cumulative to this period.
WBS ID | Work Package | Budget (Rs) | % Complete | EV (Rs) | PV cum (Rs) | AC cum (Rs) | CV (Rs) | SV (Rs) | CPI | SPI
1.1 | Site mobilisation and enabling works
1.2 | Site office, stores and labour accommodation
2.1 | Excavation and earthwork
2.2 | PCC and footings
2.3 | Foundation RCC up to plinth
2.4 | Plinth beams and backfilling
3.1 | RCC columns, ground to fourth floor
3.2 | RCC beams and slabs, ground to fourth floor
3.3 | Staircase and lift core RCC
4.1 | Block masonry
4.2 | Internal plaster
4.3 | External plaster and texture finish
4.4 | Flooring, vitrified tile and kota stone
4.5 | Painting, internal and external
5.1 | Internal electrification
5.2 | Plumbing and sanitary installation
5.3 | HVAC and fire fighting
6.1 | External development and landscaping
6.2 | Testing, commissioning and handover
PROJECT TOTAL

## Indices
EVM Indices and Forecasts
Every cell is a formula. Compare against the tool output in docs/04-validation-report.md.
# | Measure | Formula as applied | Period 5 | Period 6 | Unit
1 | Budget at completion (BAC) | Sum of all work package budgets |  |  | Rs
2 | Planned value (PV) | Cumulative time-phased budget to date |  |  | Rs
3 | Earned value (EV) | Sum of (% complete x budget) |  |  | Rs
4 | Actual cost (AC) | Cumulative cost booked to date |  |  | Rs
5 | Cost variance (CV) | EV - AC |  |  | Rs
6 | Schedule variance (SV) | EV - PV |  |  | Rs
7 | Cost variance % | CV / EV |  |  | %
8 | Schedule variance % | SV / PV |  |  | %
9 | Cost performance index (CPI) | EV / AC |  |  | ratio
10 | Schedule performance index (SPI) | EV / PV |  |  | ratio
11 | Percent complete | EV / BAC |  |  | %
12 | Percent spent | AC / BAC |  |  | %
13 | Percent scheduled | PV / BAC |  |  | %
14 | Earned schedule (ES) | Baseline time at which PV equals current EV |  |  | periods
15 | Actual time (AT) | Periods elapsed at the data date |  |  | periods
16 | Schedule variance, time SV(t) | ES - AT |  |  | periods
17 | Schedule performance index SPI(t) | ES / AT |  |  | ratio
18 | EAC method 1 | BAC / CPI |  |  | Rs
19 | EAC method 2 | AC + (BAC - EV) |  |  | Rs
20 | EAC method 3 | AC + (BAC - EV) / (CPI x SPI) |  |  | Rs
21 | EAC method 4 | AC + (BAC - EV) / (0.8 CPI + 0.2 SPI) |  |  | Rs
22 | ETC (on EAC method 1) | EAC1 - AC |  |  | Rs
23 | VAC (on EAC method 1) | BAC - EAC1 |  |  | Rs
24 | TCPI to BAC | (BAC - EV) / (BAC - AC) |  |  | ratio
25 | TCPI to EAC1 | (BAC - EV) / (EAC1 - AC) |  |  | ratio
Notes
1. Rounding is applied by the cell number format only. No value is rounded in the calculation chain; rounding an intermediate index moves EAC method 3 by tens of rupees.
2. Earned Schedule assumes planned value accrues linearly within a period. Over a monthly period on building work this is a mild assumption.
3. TCPI to EAC1 must equal CPI exactly. It is an algebraic identity and a check that the forecast chain is intact.
4. EAC method 2 implies VAC equal to the cost variance already incurred. Also an identity.